## Project Schedule (Template View
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Job Description Intelligence and Market Insights (2023–2024)
PROJECT MANAGER | Team 19 (Rachit, Dheeraj, Sanjeet, Mohammed)
PROJECT DELIVERABLE | NLP extraction + dashboards + API prototype + final report
SCOPE STATEMENT | Extract structured info from job posts; analyze trends by region/skill; integrate SQL & dashboards
START DATE | 2025-11-10 | END DATE | 2025-12-08 | OVERALL PROGRESS | 100%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Scrape or collect LinkedIn job postings data | Mohammed Abdul-Ameer | 2025-11-10 | 2025-11-12 | 3 | Complete | LinkedIn job data scraped & collected
Clean and preprocess job data | Mohammed Abdul-Ameer | 2025-11-13 | 2025-11-16 | 4 | Complete | Data cleaned & preprocessed using PySpark
TF-IDF + Logistic Regression Baseline | Sanjeet Srinivasa | 2025-11-10 | 2025-11-16 | 7 | Complete | Accuracy & macro-F1 on 10k subset; logs & artifacts in GitHub
Skill Extraction (spaCy patterns / OvR) | Sanjeet Srinivasa | 2025-11-17 | 2025-11-23 | 7 | Complete | Precision/recall reported for skills
Create frontend application | Rachit Patel | 2025-11-20 | 2025-11-23 | 4 | Complete | User inputs processed; entities highlighted; insights generated successfully
FastAPI Inference Endpoint | Rachit Patel | 2025-11-24 | 2025-11-27 | 4 | Complete | Endpoint returns structured JSON
Dashboard (skills/region/salary) | Dheeraj Royal Galla | 2025-11-24 | 2025-11-30 | 7 | Complete | Top skills, locations & salary distributions
Unit & API Testing + Perf Tuning | Rachit Patel; Mohammed Abdul-Ameer | 2025-12-01 | 2025-12-05 | 5 | Complete | Latency target & error handling; unit/API tests green
Dashboard Refinement & Final Figures | Dheeraj Royal Galla | 2025-12-01 | 2025-12-07 | 7 | Complete | Final visuals ready for report
Overleaf Final Report (methods/results/limits) | All | 2025-12-08 | 2025-12-08 | 1 | Complete | PDF export; citations & appendix
Slides & Demo Video | All | 2025-12-08 | 2025-12-08 | 1 | Complete | 5–8 slides; short demo video
Final GitHub Push & Canvas Submission | All | 2025-12-08 | 2025-12-08 | 1 | Complete | Repo up to date; Canvas submitted

## Owner Roles
Name | Role | Primary Responsibilities
Rachit Patel | Software Engineer | System integration, API development (FastAPI), React Frontend UI Development, CI/testing
Dheeraj Royal Galla | Data Analyst | EDA, insights, dashboards (Matplotlib/Seaborn/Plotly), trends by region/skill
Sanjeet Srinivasa | ML Engineer (NLP) | spaCy/BERT pipelines, classification, skill extraction, evaluation
Mohammed Abdul-Ameer | Data Engineer | Data quality, ETL/standardization, schema & SQL integration, backend data services

## Updated Timeline (Aligned)
Week | Dates | Focus Area | Tasks / Deliverables | Owner(s) | Status | Due Date | Dependencies
Week 9 | Nov 10 – Nov 16, 2025 | Baselines + Schema/SQL integration | Finalize cleaning & tokenization; design ER schema (Job/Skill/Company); SQL tables & load; TF‑IDF+LR baseline; metrics logged; GitHub push. | Mohammed (Data Engr), Sanjeet (ML) | Planned | 2025-11-16 | Dataset cleaned; initial EDA
Week 10 | Nov 17 – Nov 23, 2025 | Transformer fine‑tuning (BERT) + Skill extraction | Fine‑tune BERT for role classification; skill extraction (spaCy patterns/OvR); compare vs baseline; checkpoints & eval scripts; update data dictionary. | Sanjeet (ML), Mohammed (Data Engr) | Planned | 2025-11-23 | Week 9 baseline & SQL schema
Week 11 | Nov 24 – Nov 30, 2025 | API & Prototype | FastAPI endpoint for inference; React Frontend UI; Plotly dashboards (skills, salary, hotspots); demo dataset. | Rachit (SW), Dheeraj (Data Viz) | Planned | 2025-11-30 | Best model from Week 10; SQL access
Week 12 | Dec 1 – Dec 7, 2025 | Testing, performance & polish | Unit & API tests; latency/perf tuning; error handling; refine dashboards; freeze figures & tables; readiness checklist. | Rachit (SW), Dheeraj (Viz), Mohammed (Data Engr) | Planned | 2025-12-07 | API + prototype + dashboards
Week 13 | Dec 8 – Dec 14, 2025 | Final report & submission | Overleaf report; slides & demo video; final GitHub push (scripts, schema, notebooks); Canvas submission. | All | Planned | 2025-12-14 | All prior milestones complete

## Milestones (Aligned)
Milestone | Target Date | Owner(s) | Acceptance Criteria
ER Schema + SQL integration complete | 2025-11-16 | Mohammed | Tables created & populated; diagram exported; queries validate rows
Baseline TF‑IDF+LR ready | 2025-11-16 | Sanjeet | Macro‑F1 reported on 10k; artifacts & logs in GitHub
BERT fine‑tuned + skill extraction | 2025-11-23 | Sanjeet | BERT > baseline; precision/recall for skills
API + Prototype (FastAPI + Streamlit) | 2025-11-30 | Rachit, Dheeraj | JSON output from endpoint; dashboard views live
Tested pipeline & refined visuals | 2025-12-07 | Rachit, Dheeraj, Mohammed | Unit/API tests pass; latency target; figures finalized
Final Overleaf PDF + Slides + Canvas | 2025-12-14 | All | PDF, slides, video; GitHub updated; Canvas submitted