## Sheet1
Epic | User Story | Status | Assigned To
Data Collection & Preprocessing | Scrape or collect LinkedIn job postings data | Done | Mohammad
Data Collection & Preprocessing | Clean and preprocess job data | Pending | Mohammad
Data Collection & Preprocessing | Store processed data in structured format (CSV/JSON/DB) | Pending | Mohammad
NLP Model Development (spaCy) | Explore spaCy pre-trained models for job-related entities | Pending | Sanjeet Srinivasa
NLP Model Development (spaCy) | Fine-tune or add custom entity types (Experience, Education, etc.) | Pending | Sanjeet Srinivasa
NLP Model Development (spaCy) | Visualize extracted entities to validate performance | Pending | Sanjeet Srinivasa
NLP Model Development (spaCy) | Evaluate model accuracy using labeled samples | Pending | Sanjeet Srinivasa
Backend Development | Build REST APIs for job and entity data | Pending | Rachit Patel
Backend Development | Integrate spaCy NER model with backend | Pending | Rachit Patel
Backend Development | Implement pagination or batching for large datasets | Pending | Rachit Patel
Frontend Development (Web App) | Allow users to upload/select job descriptions | Pending | Rachit Patel
Frontend Development (Web App) | Display extracted entities with highlighting | Pending | Rachit Patel
Frontend Development (Web App) | Show summarized insights (top skills, companies, roles) | Pending | Rachit Patel
Frontend Development (Web App) | Add responsive UI and filters | Pending | Rachit Patel
Integration & Deployment | Containerize the app with Docker | Pending | Rachit Patel
Integration & Deployment | Deploy on AWS / Render / Vercel | Pending | Rachit Patel
Integration & Deployment | Setup GitHub CI/CD pipeline | Pending | Rachit Patel
Integration & Deployment | Add logging and error handling | Pending | Rachit Patel
Analytics & Reporting | Show frequency distribution of skills, job titles, and companies | Pending | Dheeraj Royal
Analytics & Reporting | Allow users to download reports (CSV/Excel) | Pending | Dheeraj Royal
Analytics & Reporting | Add data visualizations (charts/graphs) | Pending | Dheeraj Royal
Documentation & Testing | Create README and setup guide | Pending | Dheeraj Royal
Documentation & Testing | Write unit tests for main components | Pending | Dheeraj Royal
Documentation & Testing | Conduct usability testing for the web app | Pending | Dheeraj Royal